## Hoja1
no | description | duration | predecessors
1 | Proposals work | 7 | 0
2 | Literature Review on Anomaly Prediction and State of Art | 42 | 1
3 | Design Experiments on Anomaly Detection | 35 | 2
4 | Refine Code including MetaHeur. to feat. selection | 56 | 3
5 | Obtain anomaly samples -Artificially? (Trial rig?) | 56 | 4
6 | Run experiments | 35 | 5
7 | Analyze Results | 21 | 6